## Slide 1
A monthly leadership control point for priority, ownership, sequencing, material dependencies and evidence-based progression.
The steer prioritises outcomes and Discovery capacity — it does not approve a technology solution before the process is understood.
What leaves the meeting?
Return-to-Steer date
Next evidence / milestone
Accountable owner
Agreed priority / route
Confirm Portfolio
Position
What should happen to each
candidate?
Decision 2: Mobilise
approved Discovery
Decision 1: Priority & Route
Make Stage 2
Decisions
What new process outcomes
need consideration?
Existing initiatives or
capabilities
Problem / outcome /
ownership
Stage 1 candidate briefs
Review New
Candidates
What is already underway?
Items returning for decision
Capacity and dependencies
Material progress / issues
Active initiatives and current
stage
Review Current
Portfolio
Part 2 Monthly Steer
Monthly MRO FDE / Tech & Tooling Steer
Prioritise MRO process outcomes, mobilise focused FDE Discovery, and oversee material
decisions across the active Tech & Tooling portfolio.
1
MRO FDE / Tech & Tooling Monthly Steer

## Slide 2
The steer should consider current commitments before adding new priorities.
Material scope, timing or
ownership changes
Attention items
Decision Required items
Leadership attention
Process owner / SMEs
Data / access
Platform
Material dependencies
SME capacity
Engineering capacity
FDE capacity
Capacity
Leadership Focus This Month
Current commitments and capacity provide the context for deciding whether new Discovery should start now.
On Hold
Decision Required
Attention
On Track
Status key:
On Hold
TBD
TBD
Other active
initiative
Attention
To confirm
Improve classification
workflow
MRC Assistant
Next steer
On Track
Stage 5 —
Experiment
Improve validation
code review
Code Review
Assistant
Outcome
Initiative
TBD
TBD
Next steer
Confirm stage /
next milestone
PoC / vertical-slice
results
Return to
Steer
Next Evidence /
Decision
Status
Current Stage
Active Portfolio
Review existing commitments and material constraints before deciding what new work should start.
Monthly Steer
Part 2
Current Active Portfolio & Capacity Context

## Slide 3
Which candidates need individual discussion today?
Stage 1 creates comparable process/outcome briefs — not technology approvals.
New
TBD
TBD
TBD
Other IVT
Candidate 4
New
TBD
TBD
TBD
Other IVT
Candidate 3
Existing capability
Existing overlap
MRM Policy Chatbot +
tactical tool
To confirm;
Edidiong / Guy SMEs
Improve policy access;
reduce repetitive SME
support
Matt / CBPM IVT
MIAMI Policy &
Guidance Support
Ready for Steer
Templates and report
guidance
To confirm;
Cheng proposed
Reduce drafting effort;
improve consistency and
guidance use
Matt / CBPM IVT
IV Report Drafting &
Quality Review
Existing Work /
Capability
Proposed Process
Owner
Source / Team
Candidate Process /
Outcome
Stage 1 Intake View
Problem / Desired Outcome
These candidates have passed lightweight intake and are ready for Leadership consideration or routing.
Part 2 | Monthly Steer
New Candidate Backlog — Stage 1 Outcomes

## Slide 4
4
MRO FDE / Tech & Tooling Monthly Steer
Treat the proposed AI assistant as a solution hypothesis; Discovery first validates the reporting process, requirements and opportunities.
FDE consideration: assess MRO / M365 capability
before new build
Existing related reporting material
IV report-writing guidance
Existing IV templates
Existing Capability Identified
FDE Intake View: Ready for Stage 2 prioritisation. If prioritised, Discovery should understand where report-writing effort,
inconsistency and guidance-use issues arise before confirming the appropriate intervention.
Users: IV authors and reviewers
Formal Process Owner: to confirm in Stage 2
Julian suggested as supporting framing
Proposed Owner / SME: Cheng Cheng
Source: Matt / CBPM IVT
Owner / SMEs / Users
Solution hypothesis — not yet agreed route
Highlight outstanding gaps to the IV author
Suggested ambition: 60–80% complete
Produce a substantially complete IV report draft
AI-assisted use of Q&I logs, annotated MDDs, emails and
Teams messages
Proposed Outcome / Solution Concept
Guidance updates may not consistently inform report
writing
Latest template may not always be used
Risk of inconsistency across MRO
Drafting an IV report takes significant time and effort
Current Process Problem
Part 2 | Monthly Steer
Candidate Brief — IV Report Drafting & Quality Review
Use case: Support the drafting and quality review of IV reports.

## Slide 5
Decision 1 should leave the case with a clear route, accountable Process Owner and Discovery timing.
1
SLT is prioritising the IV reporting outcome and deciding its route —
not approving an AI drafting tool.
i
Conditions / Notes
Discovery Timing
Relative Priority
Process Owner
Leadership Sponsor
Decline
Combine
Route Elsewhere
Hold
Route to Existing Initiative
Prioritise
Decision
SLT Decision Record
Improvement opportunity remains unrealised
Consistency / guidance-use issues may persist
Manual drafting effort continues
No-action consequence
MRO / M365 capabilities to assess
Report-writing guidance
IV templates
Existing Work / Capability
Wider IVT applicability — to validate
Project delivery agility
Guidance / template adherence
Potential inconsistency across MRO
Significant drafting effort
Why it matters
Proposed AI assistance remains a solution hypothesis.
Improve IV report drafting and quality-review efficiency,
consistency and use of current guidance.
Outcome
Leadership Assessment
Part 2 Monthly Steer
Decision 1 — IV Report Drafting: Priority & Route
What should MRO do with this candidate now?
CORE MESSAGE

## Slide 6
Start with one practical wave; allow Wave 1 to progress when sufficiently evidenced, while its learning informs later waves.
Wave 3 — Markets IV Reporting
Wave 2 — Retail IV Reporting
Sequence agreed ≠ all waves start now.
Sequenced Future Waves — Not Yet Mobilised
Expected Return
Return-to-Steer date
Timebox
Tech / Platform input
FDE Lead
Users / SMEs
Process Owner
Discovery Mobilisation
Where does material drafting
and review effort arise, what
evidence and professional
judgement are required, and which
parts of the reporting workflow
could be simplified or technology-
enabled without weakening
validator accountability?
Discovery Question
Prioritised — Discovery now
Improve IV report drafting
and quality-review efficiency,
consistency and guidance use.
Prioritised Outcome
Wave 1 — Mobilise now
Commercial Banking &
Portfolio Modelling (CBPM)
IV Reporting
Current Discovery —
Initial Wave
Only completed where
Decision 1: Discovery Timing = Now
For candidates approved to start Discovery now:
where should FDE start, what must it learn, and when should findings return?
Monthly Steer
Part 2
Decision 2 — Mobilise Approved Discovery

## Slide 7
The monthly steer leaves the portfolio with clear priorities, owners, sequencing and evidence-based next steps.
Items returning next month
Unresolved dependencies
Leadership Attention
Routed to existing capability
Discovery later
Sequenced / Routed
Active work continuing
New Discovery mobilised
Started Now
Portfolio Position After This Steer
A steering decision is complete only when the route, accountable owner, next evidence and return point are clear.
TBD
TBD
TBD
Active initiative
Next steer
To confirm
Continue
Active initiative
Next steer
Capability / routing
assessment
To confirm
Route / align to
existing capability
New candidate
Next steer
To confirm
New candidate
Accountable
Owner
TBD
Other initiative
Stage 5 results
Code Review
Assistant
MIAMI
Guidance
Stage 3 Discovery
findings / Opportunity Map
Prioritised —
Discovery now
IV Report
Drafting
Return to
Steer
Next Evidence /
Milestone
Agreed Position
Type
Item
Record what was agreed, who owns the next step, what evidence is required and when it returns to the steer.
Part 2 | Monthly Steer
Monthly Steering Decisions & Next Evidence